## Sheet1
Team: B3T
28-4-2021: Start our project, we began to analize requirements and find ideas for the website
Then I created a list of tasks and divided it up to each members of the group, and we started analyse and build the database.
Application part | Coder | Content | Status | Start date | Duration
Database (project semester) | Nguyen Hoang Bich | Analyse, create tables and add data. | Done | 2021-04-28 | 15 days
Database (project semester) | Hoang Minh Tien | Check database relation, fix and change some tables. | Done | 2021-05-15 | 10 days
Admin Template
Admin interface | Nguyen Hoang Bich | Design effects, contents, interface for admin | Done | 2021-04-30 | 20 days
_Admin - Home | Nguyen Hoang Bich | Display profile,account and design edit function. | Done | 2021-05-01 | 5 days
_Admin - Account objects | Nguyen Hoang Bich | Display list account objects, design add, edit and delete functions. | Done | 2021-05-06 | 2 days
_Admin - Banks Account | Nguyen Hoang Bich | Display bank accounts, design add, edit and delete functions. | Done | 2021-05-08 | 3 days
_Admin - banks | Nguyen Hoang Bich | Display banks, design add, edit and delete functions. | Done | 2021-05-09 | 1 day
_Admin - Currencies | Nguyen Hoang Bich | Display currencies, exchange from api, design add, edit and delete functions. | Done | 2021-05-11 | 2 day
_Admin - FAQ | Nguyen Hoang Bich | Display frequently asked questions, design add, edit and delete functions. | Done | 2021-05-12 | 1 day
_Admin - Customer Question | Nguyen Hoang Bich | Display customer question and answer function | Done | 2021-05-14 | 2 days
SuperAdmin - Setting | Nguyen Hoang Bich | Display setting, design edit functions. | Done | 2021-05-19 | 5 days
SuperAdmin - Staff | Nguyen Hoang Bich | Display staff list design add, edit and delete functions. | Done | 2021-05-24 | 3 days
SuperAdmin - Help Info | Nguyen Hoang Bich | Display help info, design edit functions. | Done | 2021-05-27 | 1 day
Login Template
Login template | Hoang Minh Tien | Design effects, contents, interface for login | Done | 2021-04-30 | 5 days
_Login - Login page template | Vu Thi Thom | Design login page and display content of login page | Done | 2021-04-30 | 3 days
_Login - Login page | Hoang Minh Tien | design login function and and lock the account when the user logs in wrongly 3 times | Done | 2021-05-04 | 2 days
_Login - Authenticator | Hoang Minh Tien | Display content of authentication page and design a function to protect accounts by two-step authentication with Time-Based One-Time Password | Done | 2021-05-06 | 3 days
_Login - Forgot password | Hoang Minh Tien | Display content forgot password page, design a function that checks the information and provides a new password | Done | 2021-05-09 | 1 day
_Login - Sign-up | Hoang Minh Tien | Display content of sign-up page and design check, add functions | Done | 2021-05-10 | 1 day
User template
user interface | Vu Thi Thom | Design effects, contents, interface for user | Not Completed | 2021-05-02 | 7 days
user interface | Hoang Minh Tien | Design effects, contents, interface for user | Done | 2021-05-09 | 5 days
_User - Profile | Hoang Minh Tien | Display profiles and design edit function. | Done | 2021-05-11 | 1 days
_User - Setting | Hoang Minh Tien | Display content of setting page and design edit functions | Done | 2021-05-12 | 2 days
_User - Home | Hoang Minh Tien | Display content of home page and design add functions | Done | 2021-05-14 | 2 days
_User - Report | Vu Thi Thom | Design edit, add report function | Done | 2021-05-16 | 7 days
_User - Account | Vu Thi Thom | Display content of account page and design search function | Done | 2021-05-23 | 7 days
_User - Transaction | Hoang Minh Tien | Display content of transaction page and design add,edit,verify function | Done | 2021-05-19 | 5 days
_User - Contact | Hoang Minh Tien | Display contact detail and design add function | Done | 2021-05-20 | 1 day
_User - User manual | Vu Thi Thom | Display content of user manual page | Done | 2021-05-23 | 3 days
Support & Rating | Vu Thi Thom
Tester | Nguyen Hoang Bich | Test all function of the admin
Tester | Hoang Minh Tien | Test all function of the login and user
Reporter: Hoang Minh Tien